## Slide 1: Financial Systems Modernization
Executive Sponsor Briefing
March 23, 2020
Mark Schulz
Deputy CIO

## Slide 2: Agenda
Phase II – FAMIS Replatforming project status update
  Workstream highlights
  Enterprise Performance Management
Reporting Enhancements project update
Questions and roundtable discussion

## Slide 3: Project Phases
Proof of concept to replatform FAMIS
COMPLETE
Replatform FAMIS
February 2020 – February 2022
Modernize FAMIS
February 2022 – February 2024
Reporting Project
Notes: Phase I – Proof of concept to replatform FAMIS – complete
Phase II –Replatform FAMIS
Phase II – FAMIS Modernization
Throughout Phase II and Phase II is the Reporting Project.

## Slide 4: Phase II
FAMIS Replatforming

## Slide 5: Phase II Timeline
February 2020 | Kick-off
July 2020 | All FAMIS code converted to new programming language
October 2020 | All account and user data converted
June 2021 | System integration testing finishes
December 2021 | User Acceptance testing finishes
February 2022 | Replatformed FAMIS available for use

## Slide 6: Phase II Status Update
System Offices staff shifts to primarily working remotely
No plan to adjust project timeline at this time
Current activities on track
Change order with Asysco to add project manager
  Nate Bignall has joined Asysco
    Formerly a client of Asysco and a project manager for a similar project
    US based
    Working with procurement to issue change order
Notes: Currently, the A&M System Offices has asked that all non-essential personnel work from a remote location and all essential personnel work remote if possible. While this has caused some disruption, it has not stopped progress on the project. In addition the travel ban for our European consultants has caused some disruption, but again not stopped progress. Activities are still on track.

## Slide 7: Workstream Highlights
Natural code remediation progressing
BMC Control-M order is in process
  Process scheduling software
Database design and data conversion has begun
Canopy framework under development

## Slide 8: Workstream Highlights continued
Manage File Transfer RFP to be issued soon
  Document is with procurement
Printing
  Order in discussion with LRS for remote printing support
  Initiative to eliminate all centralized printing
UIN migration
  All UIN services off mainframe
GASB 87 impact on FAMIS

## Slide 9: Asysco Update
Factory Certification (Code, Data & JCL Migration):
  Code = 96.27%
  Data = conversion complete. Fine tuning the model to meet with expectation. This proposed model will be shared by the end of this month.
  JCL = 98.31%
Note - Remediation effort from TAMUS team has been excellent and reduced the number of conversion errors significantly
No major blockers or concerns at this time
Completion date for all of the above on May 31, 2020
Development work continues for Shadow Server, ESS, SQL Gateway etc

## Slide 10: Asysco Update
New Project Manager: Nate Bignall
Officially started today
He is assigned to the TAMUS project 100%

## Slide 11: Enterprise Performance Management (EPM)
The A&M System is using the term EPM to describe our search for software to enhance FAMIS in the following areas
Financial close, consolidation and related reporting
Planning and budgeting
Financial forecasting

## Slide 12: Reporting Enhancements Project

## Slide 13: Reporting Enhancements Project Update
Accenture statement of work
  Can project be split into two phases?
  One phase – technical review – remote work acceptable
  2nd phase – begins when onsite visits can resume
Workday Prism agreement in place
  1st Engagement: Pre-payroll validation dashboard
  2nd Engagement: Employment changes
Workday Prism demonstration

## Slide 14: Questions and Roundtable Discussion