## Slide 1: Financial Systems Modernization
Executive Sponsor Briefing
September 28, 2020
Mark Schulz
Deputy CIO

## Slide 2: Agenda
Phase II – FAMIS Replatforming Project status update
  Workstream highlights
  Testing update
  Upcoming milestones
Phase III update
  AFR discovery
Asysco update
Reporting Enhancements Project update
  Prism update
  People Analytics update
  Reporting assessment summary
Questions and roundtable discussion

## Slide 3: Phase II – FAMIS Replatforming Project Status Update

## Slide 4: Phase II Timeline
February 2020 | Kick-off
June 2020 | All FAMIS code converted to new programming language
October 2020 | Final data conversion model tested and complete
December 2020 | All factory testing complete
June 2021 | System integration testing finishes
December 2021 | User Acceptance testing finishes
February 2022 | Replatformed FAMIS available for use

## Slide 5: Workstream Highlights
BMC Control-M installation and implementation in progress
  Installation complete on Development and in process on Production
  Plan for changeover to full usage set
  Installed and available for system integration testing in January
Database design and data conversion
  Second version of database is complete and in use
  Additional program changes identified
Canopy framework nearing completion
  Technical smoke testing complete and Shadow replacement delivered
  Initial business process testing has been recorded

## Slide 6: Workstream Highlights continued
Managed File Transfer RFP
  GoAnywhere from HelpSystems selected
  Proof of Concept preparations complete
Implementing TeamDynamix to improve customer service delivery
  Office of IT service management tool to track
    Requests for new items
    Reports of something not working
    Pattern of failures
    New project requests
    On-going projects

## Slide 7: Testing Workstream
First phase - Factory Certification – a “smoke” test - Complete
Second phase - Factory Exit
  On track for December 2020 completion
  Verify mainframe conversion is successful
  Eight test recording bundles with over 200 test cases of increasing complexity
  Test execution happening with weekly improvements from root cause analysis
  Smoke testing for critical integrations like Canopy, Control-M and SQL gateway
Third phase - System Integration Testing
  Planned to begin January 2021 and complete June 2021
  Will include testing of each type of integration to ensure communication between systems
  Will cross-reference and verify identified key business processes

## Slide 8: Upcoming Milestones – Factory Exit
Completion of Canopy development and incorporation with smoke testing
Laserfiche and printing integration
Scheduling (Control-M) testing and integration
Automation of data conversion (text files)
Maestro integration technology
New Authentication (sign on) method
  Okta project has started with a 12 week timeframe

## Slide 9: Phase III Update

## Slide 10: AFR Discovery
Procurement discussions started this fall
Vendor demonstrations to be held in spring 2021
Accenture observations
  Complex Coordination
  Significant Manual Analysis
  Limited Automation Capabilities
  Unrealized Strategic Potential

## Slide 11: Asysco Update

## Slide 12: Factory Exit Status Update
Since meeting in August there has been significant progress across numerous workstreams
Eight test bundles received to date
  Combination of Online Screens and Batch Processes
Delivery of Data Model 2.0 and acceptance documentation is on schedule
Development work on Entire System Server (ESS) and Shadow Server is complete
  Testing continues and will be delivered in October

## Slide 13: Testing Status
Only Test Bundle 1 has been analyzed and updated for acceptable differences
Online Screens | Number of Tests | Pass | Pass % | Fail | Fail %
Test Bundle 1 | 383 | 381 | 99.90% | 2 | 0.10%
Test Bundle 2 | 1936 | 1651 | 85% | 285 | 15%
Test Bundle 4 | 1208 | 802 | 66% | 406 | 34%
Batch Processes | Number of Tests | Pass | Pass % | Fail | Fail %
Test Bundle 3 | 212 | 138 | 65% | 74 | 35%
Test Bundle 5 | 68 | 60 | 88.20% | 8 | 11.80%

## Slide 14: Summary
Code remediation from TAMUS has been exceptional
Test strategy, planning and execution focused on the next major phase - System Integration Testing
Control-M is a concern at this time; no other major issues or concerns
Progress in Factory Exit continues to be strong with productive collaboration across teams
Project continues to track well

## Slide 15: Reporting Enhancements Project

## Slide 16: Workday Reporting Implementations
Prism
Project finished on time and under budget
Pre-Payroll Dashboard is live
Event Analysis Dashboard is live
Successfully completed four training webinars
People Analytics
First phase of the project is finished
Waiting to deploy until Workday releases additional features, currently in expanded pilot
Continued collaboration efforts with Workday
Workday Product asked to be in our pilot group
TAMUS influencing People Analytics development

## Slide 17: Event Analysis Dashboard
Monitor process volume by Worker
Review overall completion times
Analyze where processes slow down or get reworked

## Slide 18: Pre-Payroll Dashboard
We stopped several overpayments by using the Terminations worklet. This directly saves us money since the employee doesn’t always return overpayments.
-Engineering Payroll

## Slide 19: People Analytics
“The goal is to turn data into information, information into insight and insight into a strategic action plan”
- Dr. Giles, Texas A&M Commerce

## Slide 20: Accenture Reporting Assessment Update

## Slide 21: Reporting Assessment Summary
We asked Accenture to conduct a comprehensive review of enterprise reporting
  Analyze the current state - assess capacity, maturity, capability
  Recommendations for future state - technologically and organizationally
  What needs to change to meet near and future needs?
  The analysis was segmented into 10 areas

## Slide 22: Stakeholder Meetings
24 stakeholder meetings held
10 OIT staff members
40+ stakeholders
  Research Administrators
  Department Administrators
  Budget and Finance Administrators
  CFOs
  CIOs
  Comptrollers
  HROs
  Dean of Faculty
  Academic Analysts

## Slide 23: Technical Analysis
Evaluation of the current reporting technology configuration (BusinessObjects)
Assessment of the approach to building the entire reporting environment
Consideration and discussion of alternate approaches and technologies

## Slide 24: Functional Analysis
How are needs of different data consumer types being met?
What are the short and long term opportunities?
What is working well?
What are the gaps?

## Slide 25: Early Takeaways
More data and report curation is needed
  Many need more prepared reports
  Some need more access to raw data
Data definitions and data governance are needed to become a more strategic organization
Organization and technology changes are required to meet the needs of the stakeholders

## Slide 26: October Meeting
Accenture will present executive summary
TAMUS Office of IT will prepare a white paper with a recap of the assessment
Discussion of prioritization, roadmap, and potential projects
Budget discussion
Discussion of required partner services

## Slide 27: Questions and Roundtable Discussion