## Slide 1: Financial Systems Modernization
Executive Sponsor Briefing December 14, 2020
Mark Schulz
Deputy CIO

## Slide 2: Agenda
Phase II – FAMIS Replatforming Project Status Update
  Asysco Update
  Additional Statement of Work
Reporting Enhancements Project Update
Questions and Discussion

## Slide 3: Phase II – FAMIS Replatforming Project Status Update

## Slide 4: Asysco Status Update

## Slide 5: Current Status – Factory Exit
Completed
Execution of all eight test bundles, both online and batch
Conversion of JCL scripts, including utility analysis
Smoke testing of Shadow Solution (test bundles 9 – 12 executed)
  Documenting solution for hand-over to TAMUS in early January
Data Conversion
No online or batch processes have identified data quality related issues
Connectivity issues to historical data have been problematic, now splitting data into small ‘chunks’

## Slide 6: Current Status – Factory Exit continued
Multiple code deliveries received and converted
  Differences identified in test results
Differences in batch output are still being reviewed by TAMUS and Asysco / Anubex
Remediated code delivered on December 11 currently being passed through conversion tools
  Too early for results
Work on WYLBUR modernization has started

## Slide 7: Test Status

## Slide 8: Summary
Test Strategy, Planning and Execution focused on next major phase, System Integration Testing
Still some code remediation remains
  Changes to be delivered in early January
Despite the ongoing remote work, collaboration across teams remains very positive and productive
Factory Exit close to completion
  Known and agreed exceptions will be carried into SIT, including the remaining code remediation

## Slide 9: Additional Statement of Work
Additional Anubex and Asysco resources to address the WYLBUR problem
Has become apparent that a “like for like” approach to our operations scripts (JCL) is not feasible
Additional resources will
  Replatform and rebuild the operational scripts
  Reduce the size and complexity of the operational scripts
  Work to automate daily operator choices and steps
  Document operator decisions and practices and find ways to automate
  Ready the scripts for conversion into Windows PowerShell

## Slide 10: Reporting Enhancements Project Update

## Slide 11: Decision on Next Steps
Annual Financial Report
  Proceed with RFP to procure software
  Currently in Procurement for review and posting
Data Catalog / Data Governance
  Final product selection in process
  Will begin with key FAMIS and Workday elements
BusinessObjects license and upgrade
  Strengthen current reporting platform
  License additional CPU power
Notes: We knew that when we modernized our financial system we would need to modernize the reporting that is offered by the A&M System Office of Information Technology; show image of Finance Modernization timeline from October 2019

## Slide 12: Questions and Discussion