## Slide 1: Financial Systems Modernization
Executive Sponsor Briefing
April 25, 2022
Mark Schulz
Deputy CIO

## Slide 2: Agenda
Financial Systems Modernization
  TAMUS Update
    FAMIS Project Update
    Annual Financial Report (AFR) Project Update
  Asysco Update
  Questions/Discussion

## Slide 3: TAMUS Update

## Slide 4: FAMIS Project Update

## Slide 5: Overall Status
Detailed plan for remaining work developed
June 30 completion of all milestones is focus
Another round of User Acceptance Testing (UAT) planned for July, before year-end processing begins
FAMIS response time (performance) remains major focus
New hardware installed and operating
  Disaster Recovery (D/R) work remains

## Slide 6
Application
Ready
Readiness & Dress Rehearsals
Go Live
The Big Picture
June 30th 2022
November2022

## Slide 7: Application Ready Activities
Task Name | Percent Complete | Status | Finish
Outstanding Defect and Gap Resolution | 80% | Green | 6/30/22
Performance Testing and Updates | 60% | Green | 6/30/22
Database Model Changes | 60% | Green | 5/26/22
Job/Spool Management Tool | 95% | Green | 5/6/22
Managed File Transfer (Go Anywhere) | 75% | Green | 6/30/22
Control-M, WYLBUR, and JCL Changes | 57% | Yellow | 6/30/22

## Slide 8: Go-Live and Readiness - Activities
Task Name | Percent Complete | Status | Finish
Infrastructure, D/R Site, and load balancing | 65% | Green | 6/30/22
Security Assessment | 0% | Not Started | 7/31/22
Control-M Conversion to Windows | 20% | TBD | 5/26/22
Custom dev for difficult WYLBUR Processing | 0% | Not Started | 5/6/22
Technical Staff Training | 75% | Green | 8/31/22
User Testing and Preview | 0% | Not Started | 7/31/22

## Slide 9: Asysco/Anubex Performance Enhancements
Root Cause | Description | Percent Complete | Status
RC-1 | Redefines | 100% | Green
RC-2 | Optimized Index Updates | 70% | Yellow
RC-3 | Optimize *Number | 100% | Green
RC-4 | Laserfiche Sweep (ESS) | 50% | Yellow
RC-5 | Optimize Child Table Updates | 20% | Yellow
RC-6 | Denormalized Views | 0% | On Hold
RC-7 | Histogram | 100% | Green
RC-8 | Test.Like Support | 100% | Green
RC-9 | READ/Reposition | 100% | Green

## Slide 10: Asysco/Anubex Performance Enhancements
Root Cause | Description | Percent Complete | Status
RC-10 | Job/Spool/API Optimize | 95% | Green
RC-11 | Spool Purge | 80% | Green
RC-12 | Optimize EXAMINE/TRANSLATE | 100% | Green
RC-13 | ASCII Translation Routines | 100% | Green
RC-14 | Indexed Views Optimize | 20% | Yellow
RC-17 | DISPLAY/WRITE Optimization |  | TBD
RC-19 | General Ledger File Split | 10% | Yellow

## Slide 11: AFR / OneStream Project Update

## Slide 12: Annual Financial Report Update
Progress on AFR project with EGP and OneStream continues
Design document reviewed and approved
Plan for FY 2022 AFR in OneStream on track
Data load for FY 2021 complete, validation up next
EGP to demonstrate first reports using FY 2021 data this week

## Slide 13: Asysco Update

## Slide 14: Asysco Status
All performance enhancements assigned to Asysco planned for delivery by end of May 2022
Bi-weekly code deliveries continue to incorporate changes from TAMUS and performance enhancements
System timings captured on each code delivery and compared against mainframe baseline to validate improvements
Application functionality remains consistent and stable

## Slide 15: Asysco Status
Remaining areas of focus are targeted for delivery:
  Limit updates to only changed columns – April 26
  Laserfiche Sweep & ESS Performance – May 24
  Limit Updates on PE to only updated tables – May 10
  Payroll Posting – May 10
  Improvements on reposition queries – April 26
  Logical File Splitting – GenSubLedger
    Code changes from TAMUS – May 10
    Data model changes – May 24
Notes:     Issue #4
    We need to analyse where time is being spent when processing very large files
    With the caching mechanism, the sweep seems to be able to keep up with typical workloads

## Slide 16: Asysco Summary
Performance is heading in right direction, more work required
Milestones defined against new plan
All remaining workstreams have clear ownership and workplan
Change request submitted for review
Project team remains focused and positive

## Slide 17: Questions / Discussion