## Slide 1: Financial Systems Modernization
Executive Sponsor Briefing
September 26, 2022
Mark Schulz
Deputy CIO

## Slide 2: Agenda
Financial Systems Modernization
  FAMIS Project Update
  Asysco Update
  Annual Financial Report (AFR) Project Update
  Questions/Discussion

## Slide 3: FAMIS Project Update

## Slide 4: Overall Status
FAMIS response time (performance) work complete
Finalizing disaster recovery plans and testing
Managed File Transfer implementation almost complete
Security mediation from Deloitte study in progress
Internal training with Anubex for FAMIS developers
Working on Change Management / communication
Practicing detailed cut-over plan

## Slide 5
Application
Ready
Readiness & Dress Rehearsals
Go Live
The Big Picture
June 30th 2022
November2022

## Slide 6: Application Ready Activities
Task Name | Percent Complete | Status | Finish
Outstanding Defect and Gap Resolution | 90% | Green | 10/31/22
Performance Testing and Updates | 100% | Green | 6/30/22
Database Model Changes | 100% | Green | 5/26/22
Job/Spool Management Tool | 100% | Green | 5/26/22
Managed File Transfer (GoAnywhere) | 99% | Green | 6/30/22
Control-M, WYLBUR, and JCL Changes | 99% | Green | 6/30/22
Notes: Nate says these are not necessary, they are all done.

## Slide 7: Go-Live and Readiness - Activities
Task Name | Percent Complete | Status | Finish
Infrastructure, D/R Site, and load balancing | 100% | Green | 6/30/22
Security Assessment | 100% | Green | 7/31/22
Control-M Conversion to Windows | 50% | Green | 10/31/22
Custom dev for complex WYLBUR Processing | 90% | Green | 10/15/22
Technical Staff Training | 75% | Green | 10/31/22
User Acceptance Testing (UAT 5) | 100% | Green | 7/31/22
Notes: See slide 6 notes

## Slide 8: Asysco/Anubex Performance Enhancements
Root Cause | Description | Percent Complete | Status
RC-1 | Redefines | 100% | Green
RC-2 | Optimized Index Updates | 100% | Green
RC-3 | Optimize *Number | 100% | Green
RC-4 | Laserfiche Sweep (ESS) | 100% | Green
RC-5 | Optimize Child Table Updates | 100% | Green
RC-6 | Denormalized Views (removed from scope) |  | 
RC-7 | Histogram | 100% | Green
RC-8 | Test.Like Support | 100% | Green
RC-9 | READ/Reposition | 100% | Green
Notes: See slide 6 notes

## Slide 9: Asysco/Anubex Performance Enhancements
Root Cause | Description | Percent Complete | Status
RC-10 | Job/Spool/API Optimize | 100% | Green
RC-11 | Spool Purge | 100% | Green
RC-12 | Optimize EXAMINE/TRANSLATE | 100% | Green
RC-13 | ASCII Translation Routines | 100% | Green
RC-17 | DISPLAY/WRITE Optimization | 100% | Green
RC-19 | General Ledger File Split | 100% | Green
Notes: See slide 6 notes

## Slide 10: Go-live Weekend Activities
Go-live planned to initiate on November 18, 2022
Mainframe data unload
Data Migration
Reconfigure integrations
Technical health checks
Controlled business health checks
Transaction updates (any necessary daily cycles)
Full business health check
Leadership team go / no-go decision
Notes: This is high level from Nate – no real timeframes on each activity yet

## Slide 11: Go-live Weekend Milestones
Friday, November 18
  No checks or ACHs produced
  Morning, Concur and Workday integrations are last inbound files
  End of day processes run at noon
  USAS integration runs early
  FAMIS / Canopy go off-line at 3:00 pm
  Data Migration begins at 3:05 pm (lasting approximately 24-30 hours)

## Slide 12: Go-live Weekend Milestones, continued
Saturday, November 19
  Systems and integrations brought up systematically
  Technical Team validation
Sunday, November 20
  Morning, user validation
  PM, final validation
  Evening, regular processes run

## Slide 13: Readiness Activities
Technical Team Training. Anubex was on site the past two weeks with multiple sessions conducted
Database conversion being practiced and timed
Sequential file data conversion in progress. Includes many historical files and data snapshots
Infrastructure new virtual servers being delivered and tested
Detailed planning for go-live weekend

## Slide 14: Change Management Initiatives
Five rounds of UAT introduced many FAMIS users to new system
TrainTraq courses for significant changes are ready
  New log on process
  Sort order difference
  System time out due to inactivity
Connectivity validation now active and being exercised
Continuing updates to project website
Presentations to CFOs and CIOs
Virtual Town Halls and connectivity validation planned for fall
Site visits with several members completed
Emails to CFOs with request to share broadly

## Slide 15: Dress Rehearsal Decision
Asysco and Deloitte recommend making last one or two dress rehearsals as similar to the go-live weekend as possible
TAMUS staff do not think this is possible without taking FAMIS/Canopy offline on another Friday in October
The best Friday/weekend for the technical team is October 21 to 23, but this weekend is critical to the accounting teams preparing the AFR
Recommendation: TAMUS will construct dress rehearsal plans that do not involve taking FAMIS/Canopy down

## Slide 16: Asysco Update

## Slide 17: Asysco Status
Project progressing well
All performance enhancements delivered and results are positive
Moved to monthly code deliveries
Operational readiness is an area of focus
Go-Live readiness including dress rehearsal and cut-over plans are well underway and taking shape
Training delivered

## Slide 18: Asysco Summary
Nearly all workstreams have been completed
Asysco and Anubex will be on-site to support dress rehearsals and go-live events; to include post implementation support
Everyone remains focused and positive
We are in a really good place right now as we approach the final phase of the project

## Slide 19: AFR / OneStream Project Update

## Slide 20: Annual Financial Report Update
Progress on AFR project with EGP and OneStream continues
  Pilot project progressing
  Data for FY 2022 being loaded daily
Some challenges remain with cash flow statement

## Slide 21: Next Meeting – October 24

## Slide 22: Questions / Discussion