## WD Roadmap Jun, Jul Aug
Task ID | Task Name | Task Description | Workday Area | Planned Release Date | HCM Advisory Council Priority
| Integration of The Texas Division of Emergency Management | Under the provisions of the Texas Legislature House Bill 2794, the Texas Division of Emergency Management (TDEM) will be transferred from the Department of Public Safety (DPS) to the Texas A&M University System as an agency of the Texas A&M University System on September 1, 2019. The Workday Services Team is currently preparing for this trasfer of employees which will consume resources and time through September | All | 2019-09-01 | Priority 1
CHG02545 | Modify routing rules on voluntary terminations | Request to add a review step to the HR Partner security role when a voluntary termination is initiated, but the user indicated the terminating employee as not eligible for rehire. This will be for all worker types - Faculty, Staff, Temp/Casual, Student Worker and Graduate Assistant | Staffing | 2019-07-18 | Priority 2
CHG00036 | Add Conditional To Do Step in Change Job and Add Additional Job Business Processes | Add a To Do step to the Absence Partner security role for the rare occasion that a person who previously retired from a non-TAMUS state agency is hired in a TAMUS entity as a student or temporary/casual employee, then later transfers, promotes or is reclassified to a benefits-eligible position. The To Do step is to move any service time earned in the non-benefits eligible position to the retirement service plan which is used to determine accruals for working retirees | Staffing | 2019-08-01 | Priority 2
CHG02945 | Configure benefits for new Custom ID for "Ready to Retire" | This request came from the Workday Benefits Working Group. There is a delay between the time that an employee meets with their Benefits Office regarding their plans to retire and the termination/retirement event being entered into Workday. This custom ID would allow Benefit Partners to proactively work with their employees before they retire and have them make their benefit elections within Workday before they walk out the door to retire. It will also allow for their retirement billing to be set up in a more timely manner | Benefits/Staffing | 2019-08-08 | Priority 1
CHG02741 | Configure to require Nationality in Personal Information | The TAMU Payroll International Tax Office and TAMUS Equal Employment Opportunity office are in agreement to require Nationality in the Personal Information business process. This change is to configure localization settings to require Nationality and edit the onscreen step help text for same. This change was presented to the Onboarding Working Group, Payroll Working Group and Staffing Working Group, who voted to support the change | Staffing | 2019-08-08 | Priority 2
CHG03004 | Implement Administrator user role in Guardian I-9 on system-wide basis | With the re-implementation of Guardian, the I-9 Working Group and Workday Services team reviewed security roles, standards and other functionality to improve the I-9 experience for employees and supporting roles. The I-9 Working Group fully supports implementing the use of the Administrator role on a system-wide basis to enable members to manage their own I-9 needs and prompt action to meet I-9 compliance. The goal will be to ave two Administrators per member who can set up new user accounts and take action to support dual-employment I-9s | Staffing | 2019-09-01 | Priority 1
CHG02944 | Create new security role - International Tax Partner | Create a new security role to support business needs of the TAMU office that oversees foreign national employment and Glacier for multiple members. Currently, these individuals were assigned Benefits Partner, Payroll Partner and View Only roles to do a few actions, without the expertise or responsibility for the overall functionality in the payroll or benefits areas. These users have needs related to demographic actions, reporting, access, errors with SSNs, etc., the new proposed security role will allow them to view and modify staffing and payroll-related tasks without compromising full access to an entire function. This will allow use of To Do steps in Change Job, Hire, Add Additional Job and other staffing events that are of critical importance when foreign national employees change Company or Location | Security | 2019-09-12 | Priority 2
CHG03002 | Change requirements on entering SSN in Onboarding | The changes in the Onboarding business process below were presented to the Onboarding Working Group, Payroll Working Group and Staffing Working Group; all three working groups support these changes. The changes are to reduce the prevalence of missing or incorrect SSNs and improve compliance with various state and federal regulations, and benefits and retirement business needs. 1. Make the Edit Government ID (SSN) step required if U.S. citizen or permanent resident 2. Make the Edit Government ID (SSN) step optional only if non-resident alien 3. Add notification to foreign national employee informing them that skipping the step does not mean the SSN is not needed and they should enter their SSN as soon as possible (language to be drafted by Payroll International Tax office) 4. Add a rule that will prohibit entering the UIN or invalid numbers instead of the SSN in the National ID section (prohibit two zeros in middle, prohibit all zeros, repeating numbers, etc.) | Staffing | 2019-09-12 | Priority 1
CHG03003 | Eliminate need to trigger Additional Data Event during Onboarding | Eliminate the need to trigger the Additional Data Event questions during Onboarding and, instead, include the questions as the last step of the Hire business process. This will assure the questions go to the employee at the same time steps in the Onboarding business process do and eliminate the need for HR Contact to receive the To Do step to trigger the questions. This change also necessitates moving the requirement for HR Contact to update Mail Stop other ID data to the To Do step "Onboarding is Complete". These changes were presented to the Payroll Working Group, Onboarding Working Group and Staffing Working Group who voted to support the change | Staffing | 2019-09-12 | Priority 1
CHG01442 | Notification when Delegate terminates | Notification to the delegating employee when a selected delegate terminates so the delegating employee can pick a a replacement person to be the delegate | Staffing | 2019-09-19 | Priority 3
FTR02598 | Add Eligible to Rehire to Report No Show business process | A new Eligible for Rehire field can be added to the No Show business process to indicate hire eligibility for a no show. The field must be configured to require on the business process. This expanded reporting capability will make it easier to identify and track hire eligibility and no show status for workers | Staffing | 2019-09-19 | Priority 3

## WD Roadmap Completed
Task ID | Task Name | Task Description | Workday Area | Planned Release Date | Comments | HCM Advisory Council Priority
CHG02325 | Allow SGIP to show for New Employees | A solution to allow new employees going through the hire process to be able to see their SGIP (employer contribution) reflected in their premiums when they do their benefits enrollment during onboarding. The change involves making all employees eligible for their eventual benefit group (ex. Full time monthly) immediately upon hire. The benefit event already enforces the appropriate waiting period. When looking at actions over the last year, around 10% of employees system-wide chose to start their benefits before their SGIP start date. For these exceptions, an action would be required by the Benefit Partner to move them into an SGIP waiting period benefit group | Benefits | 2019-02-28 | Complete | Priority 1
CHG01778 | Replacement of Time Off (Leave) report utilized in Business Objects | Request from Texas A&M International University for a custom report to enhance what is currently available through Workday standard reports. A report with balances from several months, for example Sept,Oct and Nov, would be sent to managers encouraging them to review leave their employees had earned or taken by month. Emails indicated, “If you know an employee took leave, but you don’t see a reduction for that month, please ask them if they submitted their leave.” Is this something anyone else has utilized previously or has a need for at this time? -Others indicate they think this would be a useful report | Absence Management | 2019-02-28 | Complete | Priority 3
CHG01618 | Add values to Faculty Rank job classification group | Edits need to be made to the Faculty Rank job classification values to add a value for Staff (rather than use a 'null' value) and values for Graduate Assistant Non-Teaching, Graduate Assistant Research and Graduate Assistant Teaching job profiles. The business need was discussed with the Pay Plan Administration Committee who agreed to the implementation of the formerly-used BPP attribute of 'T' to explicitly define Staff job profile This change was prompted by requests from FAMIS, Datawarehouse and Workday teams | Staffing | 2019-02-07 | Complete | Priority 1
CHG01436 | Edit compensation processes for Cell Phone Allowances | Add valdiation rules and soft warnings to comply with System Regulations 25.99 related to cell phone service and equipment payment In Request Compensation Change for Cell Phone Allowance, if the Cell Phone Service Allowance amount is more than 120.00 route to Executive Approver. This would support System policy which states the limit is 120.00, but gives the CEO or designee the ability to approve exceptions. If possible, provide a soft warning if the amount is more than 120.00 that additional approval from the Executive Approver will be required based on the fact the amount is more than system policy. In One-Time Payment for Cell Phone Equipment Allowance,if a one-time payment is for a Cell Phone Equipment Allowance have it route to the Compensation Partner. This would support compliance with System policy as it states that an employee can only be reimbursed $100 every 2 years. OR, add a validation to prohibit requesting at less than 2 year intervals, rather than routing to Compensation Partner to review for the timeframe If the Cell Phone Equipment Allowance amount is more than 100.00 route to Executive Approver. This would support System policy states the limit is 100.00, but gives the CEO or designee the ability to approve exceptions. If possible, provide a soft warning if the amount is more than 100.00 that additional approval from the Executive Approver will be required based on the fact the amount is more than system policy This request is from Texas A&M University | Compensation | 2019-02-07 | Complete | Priority 1
CHG02238 | Add three Academic Pay Period for short semester sessions | Add the following two periods to accommodate short-sessions during the normal semesters that are worked by adjunct instructors: May 1 - June 30 October 16 - December 15 October 16 - January 15 These three periods will round out the already-configured short-session periods. This request is from Texas A&M International and Texas A&M University-San Antonio | Staffing | 2019-01-31 | Complete | Priority 2
CHG01426 | Implement No Show business process | Request to add a new-to-Workday No Show business process enabling you to seamlessly rescind the hire and halt downstream processes such as payroll calculation and onboarding events for workers who don't attend their first day of work. The business process includes: • A Hire Rescinded flag used to notify downstream integrations that a worker has been rescinded • The requisition and position are reinstated • If the hire was originally completed from a recruiting event, the pre-hire record is moved to the step prior to Ready for Hire in the recruiting process | Staffing | 2019-01-31 | Complete | Priority 1
CHG00197 | Edit review and approvals based on reasons in Change Job business process | Enhance the routing for review and approval in the Change Job business process to streamline usage based on specific even reasons, e.g., changing job classification on position, changing scheduled hours, etc. Changes were reviewed and approved by the Staffing Working Group to edit condition rules based on worker type below: For Staff • Trigger an approval to Executive Approver for Change Job – Reclassifications • Trigger an approval to Executive Approver for Change Job – Demotions • Trigger a review to HR Partner for reason of Hours Change – Change For Student Worker • Remove routing to Executive Approver for Change Job – Promotion For Temporary/Casual • Remove routing to Executive Approver for Change Job – Promotion Votes from Staffing Working Groups: • Vote of 7-0 - Graduate Assistant - Leave As Is • Vote of 7-0 - Faculty - Leave As Is • Vote of 5-2 - Staff - Add Executive Approver to Reclassifications • Vote of 7-0 - Staff - Add Executive Approver to Demotions • Vote of 7-0 - Staff – Hours Change - Fix condition Rule to Route to HR Partner • Vote of 7-0 - Student Worker - remove Ex Approver for Promotion • Vote of 7-0 - Temp Casual - remove Ex Approver for Promotion Must add binary decision on Executive Approver for reclassifications | Staffing | 2019-01-31 | Complete | Priority 2
CHG02253 | Changes to Pay Frequency Change Benefit Event | Currently, a passive event triggers when an employee is moved to / from Biweekly / Monthly. This passive event "sits" in the Benefit Partner's inbox for 7 days as a reminder to work with payroll to determine if the employee needs a manual payroll correction to handle their benefit premiums. The benefit event doesn't allow any enrollment changes We would like to: -Shorten the days to enroll on the Pay Frequency Change benefit to 1 - this will allow System Benefits Administration to finalize it after one day. -Add a To Do step AFTER the completion step that would go to Benefit Partner. It would advise them that the employee changed pay frequencies and that they should work with their payroll office to ensure the correct premiums were taken | Benefits | 2019-01-31 | Complete | Priority 2
CHG02319 | Allow candidates to withdraw their application for a position through their career site. | Workday delivers a new Withdraw Application task (secured to the Internal Careers domain) that internal candidates can use to remove a job application from the recruiting process. Workday also provides a new Withdraw button that displays on job applications in the My Applications section on Candidate Home, enabling external candidates to withdraw their job application from the recruiting process. This feature update was brought to the Recruiting Working Group on 12-13-2018. The WG unanimously agreed to introduce this feature to reduce the load on the recruiter responsibility to withdraw a candidate upon request. | Recruiting | 2019-01-24 | Complete | Priority 2
CHG02392 | Change the Ready for Hire To Do steps (c) to change Self-Identification of Disability and Change My Personal Information for internal candidates to a notification | Working Group voted YES. We are proceeding and will notify/announce to the FAB. | Recruiting | 1/17/2019 | Complete | Priority 3
CHG02107 | Reorder the recruiting source list to be in alphabetical order. | This Change Request went to the Recruiting working Group on 12-13-2018 and Unanimously (8 of 10 members present) agreed to change the recruiting sources to Alphabetized. | Recruiting | 2019-01-15 | Complete | Priority 2
CHG01567 | Create report Former Employee Verification Records | State records retention schedule 3.3.011 Former Employee Verification Records requires each state agency to maintain former worker information for 75 years (AC + 75). To meet compliance, with Workday as the source of record, a report is needed to return data required by schedule 3.3.011 being five items: 1) Name, 2) Social Security Number, 3) Exacts dates of employment: 4) Last known address; and 5) Most recent public access option form. The report will be used to return data from Workday from point of conversion; prior employment information should be managed as previously done | Staffing | 2018-12-20 | Complete | Priority 2
CHG01739 | Configure Total Rewards statement for employees | Configure the Total Rewards statement delivered in Workday to be a replacement of the formerly used Total Compensation Statement. We will work with the Benefits, Payroll and Compensation teams to provide the statement for Employees in Workday. We will leverage as much of the delivered functionality as possible with the understanding that the Total Rewards statement will not be an exact replica of the formerly used Total Compensation Statement that was custom designed by the A&M System Benefits Office. The proposed availability date of the statement will be end of November | Compensation | 2018-12-13 | Complete | Priority 1
CHG01566 | Add View permission for HR Partner security role to Terminated for Conversion | Members are responsible for records retention compliance on terminated workers (AC+ 75 years). The HR Partner role needs view access to converted terminated workers to comply with the law | Security | 2018-12-13 | Complete | Priority 1
CHG01282 | Add conditional routing rule to Edit Position Restrictions | Add conditional routing rule to Edit Position Restrictions for positions in job family Research Professional - Other to route to Research Partner security role so the steps and user experience is similar to that in Create Position as requested by Texas A&M. The edits will be to add the following steps: A Review step to the Research Partner in Edit Position Restrictions if the Job Family is Research -Professional Other Trigger a Consolidated Approval step to the Research Partner security role in Edit Position Restrictions if the Job Family is Research Professional - Other *These changes were proposed by the Staffing Working Group. Discussed during Staffing Working Group on 8/21. 5-0 vote of YES | Staffing | 2018-12-13 | Complete | Priority 1
CHG01564 | New custom ID for AgriLife faculty appointment terms | AgriLife would like to track the appointment terms of Texas A&M College of Agriculture faculty who are in 12 month Academic Pay Periods, but have appointment letters at less than 12 months, so the eligibility, time off and accrual rules trigger because those faculty are eligible for vacation. They want to track what the appointment is actually a 9/3, 10/2 or 11/1. A custom ID would allow them to set the ID and report on its use within Workday. This is in lieu of configuration and eligibility changes in Absence functionality to make these faculty eligible for accruals and timeoff plans. Both the custom ID and Absence functionality changes were presented to AgriLife and they opted for custom ID. The ID could be picked up in integrations to have in Datawarehouse for reporting. The custom ID can be edited for HR Contact or HR Partner security roles. | Staffing | 2018-12-13 | Complete | Priority 2
CHG01636 | Alert / warning before submitting reviews | Working Group Recommendation: Yes, add warning on submissions Comments: - It would be nice to have a soft stop when Submitting, reminding users that edits may be needed to Save for Later instead. Specifically, edits related to the sit-down - One of the primary reasons for cancelling/re-starting reviews is submitting "by accident" - We have not reviewed if this is possible. If approved, and we can do it, we will | Performance and Goals | 2018-12-06 | Complete | Priority 2
CHG01624 | Configure a performance review template specifically for Researchers | Researchers use different competencies and have different responsibilities than what is currently on the reviews Discussion: Possibly an Attachment Only template. Researchers are more technical, do proposals and communicate and work with sponsors/donors and handle business development and career tracking based on funding WG Recommendation: 5 YES and 4 UNSURE 08/24 - HCM Advisory Council voted YES | Performance and Goals | 2018-12-06 | Complete | Priority 2
CHG02004 | Change the name of Jury Service/Court Subpoena/Summons time off | The name of the time off has caused confusion for an employee. This time off can only be used for court subpoena/summons if testimony is as an official representative of the A&M System. The employee has been called as a witness but not in their official capacity at work Suggestions are to go back to just listing "Jury Service" and those that fall into the latter category would either count it as hours worked or be advised by their Absence Partner to utilize the Jury Service time off. Alternatively, the time off name could be changed to "Jury Service/Testimony in Official Capacity" | Absence Management | 2018-11-29 | Complete | Priority 1
CHG01216 | Evaluate use of HR Contact and HR Partner security roles in staffing events | The HR Contact and HR Partner security roles have been reviewed by the Staffing Working Group and provided recommendations for configuration changes in staffing events. Their recommendations are for a more consistent and efficient approach going forward to reduce rework and inefficiencies in use and training The following business processes were reviewed by the Staffing Working Group: Create Position, Edit Position Restrictions, Hire, Onboarding, Add Additional Job, Change Job, Termination and End Additional Job | Staffing | 2018-11-29 | Complete | Priority 2
CHG02024 | Reconfigure Onboarding business process as approved by HCM Advisory Council | Review and redesign the Onboarding business process to streamline for all users and follow best practices. Work with an Onboarding Working Group to make recommendations for the redesign, get approval from HCM Advisory Council, revise job aids and provide training. The redesign will be demonstrated on October 18, 1:30 pm; WebEx information sent to HROs, Payroll Managers and the HCM Advisory Committee. Recommendations are shown in document Voting Results Onboarding Business Process 10.15.2018 | Staffing | 2018-11-29 | Complete | Priority 2
CHG02042 | Remove Switch Primary Job from Add Additional Job | There are problems being incurred in employee benefits eligibility that is caused by users switching the benefits-eligible job to the additional job when the additional job was not benefits eligible (4.5 months or more and 50% FTE or more). The Switch Primary Job has constraints in Workday functionality that prohibit retro-dating the switch in payroll has processed which then compounds the benefits. This change request is to remove the subprocess from Add Additional Job and replace it with a To Do step with clear instructions on when, why, and implications of switching primary job. Remove Switch Primary Job- Do NOT add To Do Step | Staffing | 2018-11-29 | Complete | Priority 1
CHG01161 | Update all Performance Review Templates to unhide Overall Rating during Employee Acknowledgement | Employees are not able to see the Overall Rating their Manager gives them during the Acknowledgement step Discussion: Our original understanding was that allowing the View of the Overall Rating from the employee allows visibility into the review while the manager is drafting it. We have done testing and have found that revealing the Overall Rating to the employee does not create this undesired visibility Working Group Recommendation: Allow Employees to see Overall Rating in order to acknowledge the review | Performance and Goals | 2018-11-15 | Complete | Priority 2
CHG01205 | Add validation to Attachment Only review to ensure there IS an attachment, for Managers only | Discussion: Once the Employee or Manager has completed their review and selects Submit, they will get an error requiring an attachment. The validation is for Managers only, not employees Working Group Recommendation: Add validation to Attachment Only review to ensure there IS an attachment, for managers only | Performance and Goals | 2018-11-15 | Complete | Priority 1
CHG01622 | Update all Annual Performance Review templates to allow attachments | Working Group Recommendation: 4 YES and 5 UNSURE Comments: - Currently only the Attachment Only reviews allow attachments - Adding attachments to other templates would allow for loading additional feedback, adding a separate review template even if the "incorrect" template was delivered, etc. - Would like to look into it more in the future - Attachment limitations - difficult to remove | Performance and Goals | 2018-11-15 | Complete | Priority 1
CHG02026 | Edit security for Mark Pre-Hires for Deletion | Add functionality to allow HR Partner security role to mark a duplicate pre-hire for deletion when a duplicate worker record is inadvertently created during the Hire business process. This will allow members to handle duplicate pre-hire records as soon as the duplicate action is discovered, rather than emailing Workday Services to take action. This change supports goals to decentralize work where possible when it will increase efficiently and reduce overall workload | Staffing | 2018-11-15 | Complete | Priority 2
CHG01258 | Add validation to Change Default Compensation for grade and grade profile | Add validation to prohibit the compensation grade or grade profile from being edited via the Change Default Compensation business process (to be different on Position Restrictions than that on the Job Profile) There is already a validation on the Hire business process, however, users have edited grade and grade profile using the Change Default Compensation business process. Angela Crosby confirmed that members should not change the compensation grade or grade profile on the position restrictions. It should be whatever the job profile is and if they need to change a pay grade they should go through the PPAC | Compensation | 2018-11-08 | Complete | Priority 2
FTR02051 | Update PaySlip configuration to enable overflow on PaySlip | Modify the Payroll Pay Slip configuration to include the "enable overflow on Pay Slip" feature that is apart of WD30. This feature allows for additional lines to be printed on the pay slip. Prior to this feature, if an employee had to many deductions or earnings, it would roll-up and display a cumulative amount with the wording "details not displayed". The new feature will allow the employee to view the detail with the associated cost. | Payroll | 2018-11-08 | Complete | Priority 2
CHG02052 | Remove Minor Release Form as a To Do to candidates and only have as part of the questionnaire for Recruiting Partners | The Minor's Release form is rarely needed for a position hired through Workday recruiting. If needed, the form could be done outside of Workday. | Recruiting | 2018-11-08 | Complete | Priority 1
CHG01440 | Change TDA Enrollment for new employees | All new employees are eligible to enroll in a TDA (including temp/casual and student workers). In the current configuration, the TDA enrollment is part of the Hire business process benefit events that are triggered during Onboarding Challenges with current configuration: • Benefit partner security roles are confused as to why student workers and temp/casual workers are getting a hire-benefits event • Most student workers ignore these events, and many of them terminate before their 60 days-to-enroll time period is up. These benefit events are then “unassigned” and it is left to the Workday Administrators to cancel them manually Proposed solution: • Remove “TDA Enrollment” from all Hire business process benefits events • Add a “To Do” step to the Onboarding business process (at the very end) to instruct employees on enrolling in a TDA | Benefits | 2018-10-15 | Complete | Priority 2
CHG01506 | Configure Academic Pay restriction for Allowance | Allowance plan assignments pay out unless end-dated or removed and are not configured to follow the Academic Pay Period. This causes confusion and extra work. Previously, no one had to be concerned with the annual work period. This request is to configure the compensation plans and payroll rules so that the allowance plan follows the Academic Pay Period for the position on which the compensation plan is assigned. This will allow different allowance plans, if needed, for a primary versus an additional job | Compensation | 2018-10-11 | Complete | Priority 2
CHG01726 | Prevent applicants from re-applying to Evergreen requisitions | Working Group Recommendation: Yes - Attempt configuration to prevent applicants from re-applying to an evergreen requisition. We're not sure we can do this, however, it's consistent with regular requisitions. If this is not possible, a disposition reason added from the evergreen that they are a "duplicate" Working group comments: - Similar behavior on regular requisitions - We have been required to identify candidates who have already applied to an evergreen and disposition them again | Recruiting | 2018-10-11 | Complete | Priority 2
CHG01543 | Develop report to return active Goal Setting processes | If there is a task to do Goal Setting that is still in-progress, it will prevent the launch of a performance review. This report will return those in-progress taks so they can be cleared Working Group Recommendation: This report is needed | Performance and Goals | 2018-10-04 | Complete | Priority 1
CHG01717 | Request to change Consulting - Time Off plan so that time can be granted to employees and balances can be tracked | AgriLife has requested that the Consulting - Time Off plan be changed so that hours can be granted to employees and balances tracked like Administrative time off. They require consulting hours be approved in advance for each fiscal year. This change would allow them to grant the hours that were approved and track the hours that remain. The plan is currently set up as an accrue-as-you-go plan which means when the employee's request is approved the hours are accrued and used all in one action. No granting of hours in advance is required. All system member's faculty (4.5 AWP, 50%+ FTE) and AgriLife Extension Staff (4.5 AWP, 50%+ FTE) are eligible for the plan. | Absence Management | 2018-09-27 | Complete | Priority 1
CHG01545 | Update Offer Letter language | Update offer letter language to better match needs of all members Original request: The letter refers to the University twice and as a state agency, that needs to be edited on every letter. Also, it includes the statement: You will be provided with a copy of your position description, which will contact detailed information about the duties of this position, at on-boarding. We don't normally do that. Also what are they considering on-boarding because we're trying to have them do as much on-boarding as possible prior to their start date. Does on-boarding mean their first day? Confusing. We'd like that sentence removed. Also, the letter tells them to sign and return. Most don't have scanners so they just submit. Could the signature line be removed since most applicant are not signing and returning anyway? | Recruiting | 2018-09-27 | Complete | Priority 2
CHG01534 | Update / change candidate notifications after dispositions to be more clear | The HCM Advisory Board as well as ServiceNow tickets have indicated that we need a review of all candidate notifications after a disposition out of the process. The notifications create confusion for the candidates and additional work for HR Staff Working Group Recommendations (will remain one change request for notifications and one for the evergreen validation if approved - actual wording is being drafted and will be approved by Working Group prior to change): - Internal and External dispositions need slight cleaning up on language. Changes made earlier in the year made a difference - Minimum qualifications and incomplete applications will have specific language geared toward the reason for the disposition. Incomplete applications will include contact information for HR to get help. Minimum qualifications will not refer to the HR office - Position closures will receive specific language related to that disposition. It just needs to be softened a little to show that the closure may be administrative in nature - All other dispositions, including those after interview will receive a generic "Thanks for applying, however, we are pursuing other candidates" notification. The base is already in Workday, however, the Woring Group suggested improving the wording slightly - All dispositions will receive a notification. If a member does not want to send one, they will need to wait on dispositioning candidates until they are ready for the e-mail to be sent - Remove the reference to the HR department if they have questions for all dispositions other than those listed above - Attempt to prevent applicants from re-applying to an evergreen requisition. We're not sure we can do this, however, it's consistent with regular requisitions. If this is not possible, they are requesting a disposition from the evergreen that they are a "duplicate" - Prepare a document with the candidate notifications so users know what is being sent out when they choose a particular disposition Working group comments: - I don't want e-mails going to high-level candidates (it's all or nothing behavior) - We want to contact people personally after an interview; don't want the e-mail (again, all or nothing) - Too many phone calls from candidates asking why they weren't considered - For recruiting notifications where we are asking a person to log into the external candidate home accounts, change the text "Log into your Workday candidate account" to "Log in to the application website" (or better words). It's especially confusing for terminated employees who may have both "Workday" employee accounts as well as a candidate account | Recruiting | 2018-09-13 | Complete | Priority 1
CHG01203 | Remove notifications when a goal is cancelled, denied, corrected or rescinded | Reduce number of notifications when a goal is cancelled, denied, corrected or rescinded Discussion: Managers, Talent Analyst and Talent Partners receive an Inbox notification and email to their Outlook email address every time a goal is cancelled, denied, rescinded, or corrected. For example, if supervisor denies or corrects 2 goals for one employee = 2 notifications and emails. Compound that for multiple employees. This is not very user friendly, let alone efficient or effective use of resources. Discussion Points: Notification not needed at all: Managers and Employees are part of the BP and will know when Edits are made via the Manage Goals BP Working Group Recommendation: Remove all notifications and emails for any goal editing | Performance and Goals | 2018-09-06 | Complete | Priority 1
CHG01212 | Request to add Talent Analyst to the Security Groups for Performance related reports | Report for Talent Analyst / Talent Partner security roles to review employee goals and performance. This would be changing the security on the Talent Analyst security role to have full access to view all Performance Review items Discussion: Talent Analyst security role in the past has had access; If we do this, members would need to revisit the Talent Analyst security role; Visibility would be constrained Working Group Recommendation: Yes 6, Unsure 4, No 0 | Performance and Goals | 2018-09-06 | Complete | Priority 2
CHG01402 | Updating Manage Goals business process To Do task to trigger to employees when managers edit their goals | Update Manage Goals business process To Do task to trigger to employees when managers edit their goals Description: When Managers make edits via a To Do task to goals added by an employee, no notification is triggered informing the employee a goal was edited because the To Do is configured to not fire if the employee was the initiator Discussion: Possible Solutions: 1 - Leave as is and use training to say managers need to tell employees they've made changes 2 - Remove restriction on To Do - always triggers 3 - Make Manager's employee review step a To Do instead of an action Working Group Recommendation: Remove restriction on To Do to trigger to employee | Performance and Goals | 2018-09-06 | Complete | Priority 2
CHG01539 | Remove ability from Recruiting Partner security role to see internal candidate photos | Remove ability from Recruiting Partner security role to see internal candidate photos. Concern about unconscious bias | Recruiting | 2018-09-06 | Complete | Priority 2
CHG01544 | The ability to move a candidate from requisition to another without a linked Evergreen | The frustration has come from not being able to move candidates to another requisition for a number of reasons. Currently, we only have it configured to allow moving between two requisitions linked by the same evergreen This was not discussed in July Working Group meeting - will need to determine suggestions later Approved by Advisory Council for Recruiting Partner security role | Recruiting | 2018-09-06 | Complete | Priority 1
CHG01548 | Eliminate the notification to Manager after the Ready for Hire business process has completed | Eliminate the notifications to Manager and Recruiting Coordinator security roles after the Ready for Hire business process has completed. There is a tendency once the manager receives this to perform a new action, which is not required when coming from recruiting Working Group Recommendation: Removing this notification Working Group comments: - Yes, our managers jump the gun and they often initiate a separate staffing action outside of recruiting - We believe that the staffing action (Inbox task) is sufficient notification that the department may move forward - No additional notifications to Recruiting Contacts. The fact that the staffing action may go to HR Contacts instead is likely enough to address the "need to move forward" issue. (Different change request) | Recruiting | 2018-09-06 | Complete | Priority 2
CHG01631 | Remove Government IDs and Personal Information steps from the Ready for Hire business process | Remove Government IDs and Personal Information steps from the Ready for Hire business process Working Group Recommendation (if approved, would be 2 change requests): - Remove these two steps - Move the minor's release confirmation/form to Hire and to fire even when coming from recruiting (need to work with Core HR to accomplish this) Working group comments - Poll indicates about half of respondents use this information to create UIN (not automatically - the information is taken and used with UIN manager - SSN is not required to create UIN). Others use methods used prior (calling) - Poll indicates less than 20% use this for Export Controls (primary reason they were configured). We're not sure how many candidates actually need this process performed - Ready for Hire takes an average of 3.5 days system wide. This is likely due to these steps which need to be performed by the candidate. Otherwise, it can be very quick - Candidates perform the actions but forget to submit the To Do - Candidates worry it is spam. It asks for a SSN - DOB collected determines whether or not the minor's release fires - Data here can be collected during onboarding | Recruiting | 2018-09-06 | Complete | Priority 2
CHG01803 | Add Minor Release Required questions to Hiring Checklist in the Ready for Hire business process | See CHG01631 | Recruiting | 2018-09-06 | Complete | Priority 2
CHG01655 | Add Condition Rule on Manage Certifications business process so certifications used for Absence (Time Off plan eligibility) are one and done (only Talent and Absence impacts expected) | Add condition rule to the Manage Certifications business process so when an Absence certification is used to control time off plan eligibility is added for an employee by an Absence Partner security role, it auto-approves and does not route for the Manager's approval. Remove the step to provide proof that is sent to the initiator in these instances. This would make the business process in these instances one and done | Talent | 2018-09-06 | Complete | Priority 1
CHG01189 | EMERGENCY Inactivate Compensation items in sync with eliminating Earnings Code | Inactivating certain earning codes and compensation plans effective 08/31/2018 as a result of an A&M System Earning Codes task force. It was determined these items were very infrequently used or could be accommodated by functionality within Workday for Additional Job. The items to be inactivated are: Intramural Officiating; Game Attendant; Professional Services - Medical Students; Special Programs; Recreation Sports Programs; Co-Pilots; Athletic Consulting; Tactical Officer-Corps of Cadets; Student Health Center - Radiology Reading; Student Media Task Services; Testing Specialist; Military Pay (differential from military pay); Photography Services; and Blogger. | Compensation | 2018-08-31 | Complete | Priority 1
CHG01568 | Replace To Do in Termination with Notification | Replace the To Do "Update Contact Information" with a notification to the terminating employee with the same content. The To Do was, and the notification will be, a prompt for the terminating employee to update their contact information and specifically email to help assure future access to SSO. The data reflects the employee is not taking action on the To Do step, and therefore this change will eliminate the potential that the To Do step remains in progress and the Termination process never appears to be overall complete. | Staffing | 2018-08-23 | Complete | Priority 1
CHG01718 | EMERGENCY: Remove TDAs and DCPs from Retro | Voting conducted via email and announced in August meeting. 10-0 vote to proceed forward immediately. | Payroll | 2018-08-15 | Complete | Priority 1
CHG01471 | Change number of days to enroll in benefits for new hires to 45 | Request to change the number days available for newly hired emloyees to enroll in benefits from 60 to 45 days. Most employees submit their enrollment within the first few weeks. We have encountered the issues below with employees who wait until the last week and the defaults are applied when we mass-finalize the event. Then the 60 days bumps up against the start date for the new coverage. • The passive event that runs to switch the employee from non-SGIP to SGIP runs 6 days before their SGIP start date. This is so the employee can see that the SGIP is starting. If their benefits document is not submitted by that time, it will not recognize a change and will not pick them up. They are then not given credit for SGIP unless they are manually fixed • There are some months in which the first biweekly payroll of the month is calculated the previous month (ex. March 2018 B1 was paid on March 2, and calculated on February 28). If they have not yet submitted their benefits enrollment, it cannot take their premiums out of the first bi-weekly run | Benefits | 2018-08-02 | Complete | Priority 1
CHG01480 | Payroll Partner security role to have access to enter off-cycle payment after an employee transfers | Change security to allow Payroll Partners to enter off-cycle payments for any employee, even if the employee is no longer in their Company. Also allow Payroll Partners to view payroll results for employees in other companies in order to review off-cycle payments. Payroll Partners will still not be able to modify payroll results (including off-cycle payments) for employees in another Company, they will have to work with the current Payroll Partner to correct if needed. | Payroll | 2018-08-02 | Complete | Priority 1
CHG01305 | Change security role for Review Termination if initiated from Submit Resignation | Request to change the routing of the Submit Resignation business process from HR Partner security role to HR Contact security role. The Submit Resignation business process routes to the HR Partner security role when an employee initiates Submit Resignation. TAMU would like the process to route to the HR Contact security role instead. In initial testing, there was not a means to conditional route the step if initiated from Submit Resignation. This business process change would be for all members. | Staffing | 2018-08-02 | Complete | Priority 1
CHG01477 | Disable Workday Form I-9 and reimplement Guardian | Request to disable use of Workday Form I-9 business processes and reimplement full use of LawLogix/Guardian Form I-9 effective 8/1/2018. | Staffing | 2018-08-01 | Complete
CHG01474 | Edit integrations from Workday to Single Sign On (SSO) for employee data from 14 days to 30 days for Pre-Hire | Requested by HROs at June 6, 2018 meeting, edit emloyee data integrations from Workday to SSO to be 30 days in advance of hire effective date for pre-employees to have access a full month before hire to complete onboarding. HROs will confirm any legal implications with OGC. | Staffing | 2018-07-26 | Complete
CHG01532 | In all relevant steps where this is not currently configured (Interview, Offer, Background Check), add reason “Unable to contact candidate” | In all relevant steps where this is not currently configured (Interview, Offer, Background Check), add reason “Unable to contact candidate” • TAMUG as they have had applicants who at various points in the process may not return attempts to contact. • Joni – Agree with this disposition. | Recruiting | 2018-07-19 | Complete
CHG01542 | In all relevant steps (Screen, Interview, Offer, Reference Check, Background Check), add reason “Pool contains sufficient candidates not requiring immigration-related employment sponsorship” | In all relevant steps (Screen, Interview, Offer, Reference Check, Background Check), add reason “Pool contains sufficient candidates not requiring immigration-related employment sponsorship” • TAMUG as they have had applicants who now or in the future require sponsorship for immigration-related employment authorization. They may be qualified, however the department elects to not pursue sponsorship. • Joni – Agree with this disposition. It is a legal reason for not considering an applicant. | Recruiting | 2018-07-19 | Complete
CHG01195 | Request to change the terminology "Paid Holiday" to "Paid Holiday/Early Release" on time sheet | Request to change the current terminology 'Paid Holiday' to 'Paid Holiday/Early Release' on the time as this would be a more generic category. The payroll earning name has been requested to be changed as well. | Absence Management | 2018-07-12 | Complete
CHG01204 | Update Candidate Notification Email to not refer to System Member HR Office | Current language: 'In addition, please reach out to the System Member HR office with your decision.' The term "System Member HR Office" is causing confusion when a candidate may be working with a departmental HR Contact or Manager. We propose to replace the current language with: 'In addition, please notify the hiring manager or other contact with your decision.' Due to the different needs of different members, we would need a system-wide decision to change this language. | Recruiting | 2018-07-12 | Complete
CHG01207 | Add a question to Hiring Compliance Checklist or a To Do to gather documentation related to State Veteran's Preference | Request to add an item on the Hire business process Compliance Checklist to assist in managing our responsibilities to the candidate who claims Veterans Employment Preference. With the Recruiting Partner security role To Do-Hiring Process Compliance Checklist, we would like to add a question (similar the degree verification question) asking if verification is needed for the candidate's Veterans Employment Preference status. Or, at best, if Workday could trigger a task to the candidate to supply the proper documentation, this would be terrific! | Recruiting | 2018-07-12 | Complete
CHG01208? | Further clarify the disposition reasons for "Internal Candidate" and "External Candidate" | Renamed Internal and External disposition reason to: Internal Candidate- Please Reapply (or Internal Candidate- Needs to Reapply) External Candidate- Please Reapply (or External Candidate- Needs to Reapply) | Recruiting | 2018-07-12 | Complete
CHG00160 | Implement Home and Dashboard Announcements | Configure announcements to display at the top of any Workday-delivered dashboard, custom dashboard, or landing page available on the Maintain Dashboards report. This will allow us to target the message to certain groups and to determine who receives the announcement. This will be a significant benefit to the Benefits team for open enrollment, or during merit, performance evaluations or new fiscal year news. We will be able to configure who the message is from, an expiration date, embed a video, etc. | Tenant Management | 2018-06-28 | Complete
CHG00959 | Implement New User Interface | Offered feature from Workday 29 will redesign the user interface for a better experience, enabling you to find information more quickly and expanding branding capabilities for your tenant. | Staffing | 2018-06-07 | Complete
CHG01352 | Add due Dates to Complete Form I-9 process | Edited the built-in due dates for steps within the Complete Form I-9 process so Section 1 by employee is due the hire effective date or same date the Complete Form I-9 is initiated if done as a standalone; a due date of 1 day for Review by I-9 Processor, and 3 days for Final U. S. Employment Verification status by E-Verify or by I-9 Partner. | Staffing | 2018-06-07 | Complete
CHG01355 | Re-active Resubmit Form I-9 functionality | Added functionality that allows resubmitting the Complete Form I-9 to E-Verify when there is an integration failure due to the USCIS E-Verify webservices being down or other integration failures | Staffing | 2018-05-24 | Complete
CHG01251 | Reorder To dos 1095C and Eletronic W2 in Onboarding | Reordered the To Do's Change 1095-C Printing Election and Enroll in Electronic W2 within the Onboarding business process to be in the last group of steps triggered to the employee. Workday does not allow the two actions to be done by a pre-employee, meaning the steps could cause a delay in the overall process. This change will improve efficiency of the Onboarding process. | Staffing | 2018-05-10 | Complete
CHG02257 | Rename Qatar Earnings | We would like to rename compensation and earnings items such as emoluments and allowances specifically set up for Qatar with the text “Qatar” first. We think this will benefit those in Qatar to find the allowance and one-time payments for their use only whether through a compensation business process or payroll input; and make it more obvious to people not at Qatar to avoid those. This change was reviewed and approved by the A&M System Earnings Code Task Force. See example below. Current: Education Allowance – Qatar Emolument: Inflation Differential - Qatar Proposed: Qatar – Education Allowance Emolument: Qatar - Inflation Differential Approved by HCM Advisory Council with alternative that Qatar is always listed first, e.g., Qatar Emolument: Inflation Differential; but will confirm that the A&M System Earnings Code Task Force is in agreement. If Task Force does not agree, will return to March meeting | Compensation | 2019-03-21 | Priority 2
CHG02102 | Create new job classification for Graduate Assistant Type | Create a new job classification to differentiate between the different graduate assistant workers called Graduate Assistant Type for GAR, GAT, GANT. The new ID values will be N for GANT, R for GAR, G for GAT. The Graduate Assistant value of "0" in the Faculty Rank job classification will continue to exist and not be changed. This change was prompted by requests from FAMIS, Datawarehouse and Workday teams. We will work with Angela Crosby and the Pay Plan Administration Committee to identify the job profiles to be assigned the Graduate Assistant Type. 1/15 HCM meeting Comment from Cheryl Hanks: Graduate Assistant Lecturer (GAL) needs to be added | Staffing | 2019-03-21 | Priority 1
CHG01840 | Remove department head role as initiator in business processes | The Staffing Working Group recommended during an earlier review of Create Position and Edit Position Restrictions business processes that the Department Head security role should be removed as initiator of those two business processes. This will simplify training and consistency system-wide of the business processes 6-vote of yes, 0-vote o no Security Roles who are able to initiate those processes: HR Contact, Manager, Management Chain and HR Partner | Staffing | 2019-03-28 | Priority 3
CHG02301 | Add Security Partner to business processes to allow members to approve or deny request to reassign | Requests for an item to be reassigned to someone else must be approved or denied. These are currently reviewed by Business Process Administrators (System Office Workday Administrators). Functionality is now available to allow members the ability to approve or deny requests from their employees Recommendation: Give the Security Partner role at each member this ability. This will limit the number of people who receive these additional inbox items and allow follow up if a pattern of activity is noted. For example, a change to assigned security roles may be needed if an employee is frequently reassigning. Should we give the Security Partner role the ability to approve or deny reassignment requests for their system member? 10 - Vote Yes | Tenant Management | 2019-03-28 | Priority 2
CHG01899 | Implement Verify National ID from WD31 | Implement the Verify National ID functionality (released in WD31). Verify National ID allows Employee as Self to verify their own SSN and provides for security if someone other than the employee attempts to obtain or change the SSN. | Staffing | 2018-04-04 | Priority 2
CHG02658 | Add Absence Partner approval step for Request Time Off and Correct Time Off business processes when time off is emergency | When a time off request is entered through the Request Time Off business process (by an employee or by a manager on behalf of the employee) or updated through the Correct Time Off business process for any of the following time offs: Death of a Family Member, Unsafe Working or Travel Conditions, Office Closure or Evacuation, Other Emergencies, State Military Emergency (Governor Call Up)… Recommendation: For the above situation, the manager should approve and a new approval step will be added to route to the Absence Partner for approval. | Absence Management | 2019-04-04 | Priority 2
CHG02590 | Add Absence Partner approval step for Request Time Off and Correct Time Off business processes when time off type is FMLA | When a time off request is entered or a correction to a time off is entered (by an employee or by a manager on behalf of the employee) for the following time offs: Intermittent FMLA- Concurrent with other Time Off, FMLA- Military Caregiver- Concurrent with other Time Off, or Intermittent Parental.... Recommendation: For the above situation, the manager should approve and a new approval step will be added to route to the Absence Partner for approval. | Absence Management | 2019-04-04 | Priority 2
CHG02654 | Request to allow Recruiting Coordinators request a one time payment in the Offer stage of Recruiting. | Currently Recruiting Partners and Managers are the only ones that can start the Request One-Time Payment for Offer. Recommendation: Allow Recruiting Coordinators the ability to request a one-time payment in the Offer stage of Recruiting Business Process. This change will affect all members recruiting coordinators. Requested by Ag. -=-=-=-=-=-=- This topic was presented to the recruiting working group and asked if the recruiting coordinators should be able to start a one time payment in the offer stage of the recruiting business process and enter the amount for the payment. 9 of 12 answered yes, 1 answered no and 2 did not answer. | Recruiting | 2019-04-04 | Priority 2
CHG02621 | Add validation in staffing for Time Type and Scheduled Hours | Users are not selecting time type and scheduled hours to be in sync, causing issues with other functionality and in downstream data systems. This is to add validation to Hire, Add Additional Job and Change Job so that Part Time time type must be less than 40 scheduled hours and Full Time time type must be 40 scheduled hours. This will eliminate user-created defects and confusion and provide more consistent and valid data. | Staffing | 2019-03-21 | Priority 1
CHG01986 | Edit validations and approvals for Change Job - Position Title Change | Enhance the routing for review and approval in the Change Job business process to streamline usage based on specific reasons, e.g., changing job classification on position, changing scheduled hours, etc. The Staffing Working Group reviewed and recommend the following change: • Trigger an approval to only the Manager for Change Job - Position Title Change if Student Worker or Graduate Assistant • Add validations to prohibit any other changes during a Change Job – Position Title change for Student Worker or Graduate Assistant except to the Position Title or Business Title | Staffing | 2019-04-04 | Priority 2
FTR02520 | Ability to use Project as a Worktag in One Time Payment | Before WD 32, only TAMU Cost Center was allowed as a Worktag during a One Time Payment business process. Workday now gives the ability to use Projects as a Worktag when adding One Time Payments for employees Before this feature was available, to be able to use Project as the funding source, multiple steps were required. Adding a one time payment first and then using costing allocations to make sure that the money is being funded from the correct source. With this feature, it makes the process more streamlined as the requester can select Project as a funding source if appropriate when initiating the one time payment request. | Compensation | 2019-04-18 | Priority 1
CHG02351 | Change order of subprocess in Add Additional Job business process | Change the step order in the Add Additional Job business process so the Change Organization Assignments and Propose Compensation Hire subprocesses are in the same order as in Hire. This will improve the user experience and eliminate unnecessary differences between similar business processes. | Staffing | 2019-04-18 | Priority 1
CHG02660 | Add step to the Termination business process to automatically zero out the sick time off balance 1 month past termination date | Concern: If an employee’s time off balances are not zeroed out upon termination and they are subsequently hired into a “leave eligible” position by any member, regardless of how much time has passed, the balances will reappear. Recommended Solution: Add a step to the Termination business process that will automatically zero out the sick time off balance (excluding terminations due to death). Set the step to trigger 1 month after the termination date. Discussed with Staffing working group and tested to confirm time off requests and manual adjustments can still be entered after the automated step triggers. If the employee returns before a year, there is a To Do in the Onboarding step that triggers to Absence Partners so they can restore the balance for employees that are rehired. | Absence Management | 2019-04-25 | Priority 2
CHG02460 | New Academic Pay Periods | Two new Academic Pay Periods have been requested: 1) TAMUCT has requested to add an additional academic pay period for shorter semester sessions for adjunct faculty who teach during the 8 week periods. - October 16 to December 15 2) TAMU has requested to add an additional academic pay period - March 1 to April 30 | Compensation | 2019-04-25 | Priority 1
FTR02563 | Set up External Candidate Job Alerts | We can now enable Job Alerts by external career site to automate outreach to candidates announcing specific open job opportunities. External candidates who have an candidate profile will be able to create a Job Alert with search criteria of their preference to notify them via email with matched jobs. Recommendation: Enable this feature, each member will be able to decide if they want it turned on for their external career site. The Recruiting Working Group voted 9-Yes, 2-No, and 1 did not answer | Recruiting | 2019-04-25 | Priority 2
CHG02653 | Adjust the No Retro Prior to Date to a revolving six month period | The Payroll Working Group voted to set the No Retro Processing Prior to Date for a group of workers on a revolving six month time period. By setting the No Retro Processing Prior To Date to six months, it will make the retro reports more manageable. It will still identify retro events beyond the six months, but the event will be unsupported and payroll will need to manually make the calculations and enter into payroll. | Payroll | 2019-05-02 | Priority 1
CHG02669 | Reorganize the Ready for Hire Business Process to reduce number of back to back tasks for Recruiting Partners | After previous changes to the Ready for Hire business process-removing the minor release forms and ID requests, the process was left with several steps involving the Recruiting partner and nothing in between the steps. Recommendation: Change the process into combined questionnaires and remove the repetitive step of To Do: Eligible for Hire and capture this response in the questionnaires. This change was presented to the Recruiting Working Group and asked the following things of the group: Can we consolidate the two Questionnaires in Ready for Hire Business Process 11 of 12 voted yes, 1 did not answer. Can we remove the 'ToDo: Eligible for Hire' and consolidate the function with another step. 10 of 12 voted yes, 2 did not answer Do we move forward with streamlining the Ready for Hire Business Process. 10 of 12 voted yes, 2 did not answer | Recruiting | 2019-05-02 | Priority 1
CHG02470 | Add Notification to HR Contact when Legal Name Change is approved | Request to add a notification to HR Contacts within Workday when a legal name change is approved. The concern is that HR Contacts are not aware when legal name change requests are approved and therefore do not know when to initiate email address changes and other internal updates. | Staffing | 2019-05-02 | Priority 2
CHG02556 | Edit Security on Ineligible for Rehire report and domain | Request to edit the security on the Ineligible for Rehire report so that HR Partner and Recruiting Partner can see all pre-hire records (tenant-wide) marked 'Ineligible for Rehire' when accessing the Pre-Hires Ineligible for Hire report. Currently HR Partner and Recruiting Partner security roles have access to only see ineligible Pre-Hires from their own member | Staffing | 2019-05-09 | Priority 1
CHG02252 | Add Employee as Self to routing in Edit Position Restrictions | As approved by the HCM Advisory Council in January, the Staffing Working Group evaluated the business need for Edit Position Restrictions. The Staffing Working Group recommends a new event reason called “Update Position Restrictions for Annual Review" and a new notification, instead of a step, to the Employee as Self after all approvals at the completion step when the reason "Update Position Restrictions for Annual Review" is selected. There was not agreement to route a step to employee in cases of reclassification or promotions as it may create misunderstanding | Staffing | 2019-05-16 | Priority 2
CHG02040 | Add functionality to track positions requiring risk management training | The System Offices Risk Management Office requested implementing in Workday a method to track employees in positions that require Bloodborne Pathogens and Hazard Communication training that must be assigned to employees upon initial assignment to specific job duties as per federal and state laws. The current process of using new hire reports to assign the course based on job profile or track down a Manager is labor intensive and the compliance rate is very low as per System Offices administrators. There are four potential solutions to be reviewed with recommendations from the Staffing Working Group. Note: Approved October to proceed to working group for solution with priority 1; will provide proposed solution at March 2019 meeting. Staffing Working Group recommendations, which have been approved by the A&M Risk Management office, is to add a new Job Classification for risk of exposure. See additional documentation | Staffing | 2019-05-23 | Priority 1
CHG02386 | HR Contact Access for Current Delegations report | Request to configure the security permissions for the Current Delegations report to allow the HR Contact security role to run the report | Staffing | 2019-05-23 | Priority 2
FTR02604 | Configure Request Overtime Business Process | System Regulation 31.01.09 Overtime states "All overtime for a nonexempt employee requires advance authorization. A member must have guidelines for the approval of overtime." (Section 1.2) Recently released functionality includes a new business process for workers to request and get approval from their manager for overtime before working the hours. Do you want us to configure the Request Overtime business process? | Time Tracking | 2019-05-30 | Priority 2
CHG00217 | Multiple One-Time Payments in same business process | Currently, users are only able to do one one-time payment per business process. Often there is a requirement to split the funding of a one-time payment between multiple cost centers. In this scenario, even if the payment date for the one-time payment is same, users are completing multiple business processes. Recommendation:Enabling this feature will improve flexibility and also streamline the process flow to include multiple one-time payments with different costing allocations in the same business process | Compensation | 2019-05-16 | Priority 2
CHG02786 | Update Vacation eligibility for Ag RSCH and Ag EXT | Update Vacation eligibility so that 06, 07 faculty qualify if they are 4.5 months or more and 50% FTE or more. This change is effective 9/1/2019. *Edited to remove 28. | Absence Management | 2019-06-27 | Priority 2
CHG02844 | Maintain Worktag Usage | Currently, the costing allocation will route without any cost center, worktag, being entered. This causes the payroll expense to post to the System Member's default account in FAMIS. This requires a PCT to move the payroll expense from the default account to the correct account. Modify the Maintain Worktag Usage to require a TAMUS Cost Center Worktag to be entered when completing the Assign Costing Allocation. This will stop the costing allocation from routing when the Worktag is left blank . However, if the user doesn't select "add" a row in the assign costing allocation task, it will still route without a cost center. By modifying the Worktag Usage to require a Cost Center Worktag, WD will prevent the majority of the costing allocations from routing without a Cost Center Worktag. | Payroll | 2019-06-27 | Priority 1

## WD Roadmap Canceled
Task ID | Task Name | Task Description | Workday Area | Planned Release Date | Comments
CHG01623 | Configure the Ad-hoc template for "any" employee type at member request | Working Group Recommendation: 5 YES and 4 UNSURE Comments: - During original design, we did a one-to-one mapping for templates for most members. This allowrf members to select from multiple review templates for which an employee is eligible - This would allow flexibility where there has been a change such as going from faculty to staff or the need to use an attachment-only template during annual reviews - Would solve when there is "no" annual template available or when outside the annual review period. These would be started by our managers whenever one of their direct reports are needing to be reviewed. - There are limitations to doing this. Members would need to be very aware of the templates selected and the use of those at each member | Performance and Goals | 2018-11-29
CHG01547 | Require a rating on all items in a performance review; not just Overall Rating | During design, it was decided to require only the Overall Rating, not ratings on individual items. It has been requested that we re-visit this decision. | Performance and Goals | 2018-08-30
CHG01540 | Update Candidate notifications to clarify entering through a candidate account. |  | Recruiting | 2018-08-30
CHG01187 | Test and Implement Manage Form I-9 Business Process | Workday is enhancing the Form I-9 process to accommodate multiple companies in one tenant for use with Add Additional Job and Change Job. This was a known gap in our implementation and was a delayed feature from the Workday 29 release. Workday will release the new business process to us in Preview Sandbox beginning May 25,2018 for 5 weeks for Workday Services and members to test. This process is planned for production from Workday in July. There does not appear to be any impact on integration configurations. This request is to configure and test in Preview Sandbox the functionality; will engage a representative from each System Member to test new functionality, and remediation testing as needed. Assuming satisfactory testing, implement functionality in production when released by Workday. | Staffing | 2018-06-28 | Canceled - Move to Guardian
CHG01351 | Add notification to I-9 Partner prior to 3-day rule for E-Verify | As discussed and agreed upon by the I-9 Working Group at May 15, 2018 meeting, add a notification to I-9 Partner when I-9 is still in a pending status prior to the 3-day E-Verify rule. | Staffing | 2018-06-14 | Canceled - Move to Guardian
CHG01714 | Apply Academic Pay Period to Allowance Plan payout |  | Compensation
CHG01400 | Remove Manager's Manager when Overall Rating is 1 or 2 as approval step | Request: Remove Manager's Manager when Overall Rating is 1 or 2 as approval step Description: This step in the Complete Manager Evaluation BP for Performance Reviews. Once the Manager submits an Overall Rating of 1 or 2, the next step is the Managers Manager for approval. We have had arguments that the employee should get it next in order to put their comments on the situation before it goes higher. Discussion: Option #1: Leave as is, training needed instead, add help text that tells employee when they disagree they can take these actions…HR should be prepared to talk to all involved & set up meetings #2: Add Notification to Managers Manager instead of Approval step: then review won’t stop. WG Recommendation: this should NOT change | Performance and Goals
CHG01535 | Remove Delivered Manager Card on the Team Performance Dashboard | Request: Remove Delivered Manager Card on the Team Performance Dashboard Discussion Points: This report is useful, however has led to some confusion. It will show information for staff (students/GAs) who are not eligible. No review has been launched or is required, however the report makes it seem as if it might be. WG Recommendation: Leave report as is and train managers on how to use it. | Performance and Goals
CHG01541 | Revisit using "Manager for Majority of Event" role in performance reviews | Request: Reviews trigger to Manager for Majority of Event, instead of Primary Manager When initially configured, our participants chose Primary Manager. Now that we've been through the process, we'd like to revisit this configuration. Manager for Majority of Event evaluates, in the evaluation period, who was the Manager for that employee for the majority of the time. WG Recommendation: Leave as is, Primary Manager should get reviews | Performance and Goals
CHG01625 | Training Attestation rating scale be changed from Yes/No to Yes, the employee is past due No, the employee is not past due | Request: Training Attestation be reworded; reverse from “negative” wording to positive. WG Recommendation: Prefer to change the Rating Scale, not the question; Selections would be: - Yes, the employee is past due - No, the employee is not past due Comments: - Employee must not be past due on any assigned required employee training courses. If employee is past-due on one or more assigned required employee training courses, manager and employee will discuss an action plan for the employee to complete the assigned courses in timely manner. - Current question: Is Employee past due on any assigned required employee training courses? - Request is to reverse from “negative” wording to positive. - Other option is to create a new rating system to make it clearer. -- Yes, the employee is past due -- No, the employee is not past due | Performance and Goals
CHG01635 | Remove Add Additional Manager/Reviewer steps in Performance Reviews | Request: Remove Add Additional Manager/Reviewer steps in Performance Reviews WG Recommendation: Yes, remove steps Comments: - These steps are a more of a hindrance and are not needed. - Fewer than 20% of managers are using this functionality and the remainder are skipping them. Encourage other ways of gathering feedback if needed. | Performance and Goals
CHG00180 | Design and configure standalone background check business process | Configure a business process to allow background checks to be initiated and integrated with Sterling outside of Recruiting functionality.Time is needed to design any condition rules or validations with members. The background check business process will be beneficial in cases of promotions, reclassifications, or at any time that a background check is required for business purposes May be used in the following business processes: Change Job Add Additional Job As a standalone Requires coordination with Sterling as the standalone BP functionality was not tested during implementation | Recruiting |  | Communicated process provided to the members on Sept. 12 - no configuration needed
CHG01265 | For Job Requisition approvals, it was requested that everything should be the same EXCEPT offering a binary decision of whether or not the requisition goes to the Executive Approver. | [LV - added as 3 votes in the Poll]. Evaluate use of Recruiting Coordinator and Recruiting Partner in recruiting-related events. Distributed members and Centralized members have varying needs. We need to evaluate a configuration that better matches the needs of each with regard to the recruiting process. Working Group: Request - there wasn't a specific request but rather generalized feelings from tickets that the process seems long Working group recommendations (3 - which will turn into separate change requests pending HCMAC outcome) - - For Job Requisition approvals, we agreed that everything should be the same EXCEPT offering a binary decision of whether or not the requisition goes to the Executive Approver. This BP is being used more as a permission to post than anything else. - For Job Application, we agreed that the "Screen" step should not fire individual tasks to the manager. It is especially difficult for managers with multiple requisitions and lots of candidates. That movement from screen either forward to interview or dispositioning out may be done from the grid. After that, from interview forward, we will have inbox tasks (with additional training) which should encourage managers to operate from the inbox. - For Job Application, when getting to the Staffing Action step (Hire, Change Job, Add Additional Job), we agreed that this step should also go to the HR Contact who, at larger institutions, normally performs this action. We are currently leaving HR Partner as well. There will be a future process to evaluate streamlining the entire process from Create Position (Edit Position Restrictions) through requisition, job application, hire/change job, and onboarding. There were discussion items around this during the meeting. Discussion: - We do all recruiting centrally - we're not sure we can trust our managers to handle things. We send them a matrix to fill out and we do all the movement. - Managers often mess up staffing events. We would prefer the HR Contact. - If our Department Heads and Executive Approvers have approved the position or position restrictions, they don't want to see the requisition. - Managers don't need to see the requisition. Department Heads should. - Pretty heavy discussion on routing order. We decided what is there is likely best. - Talked briefly about streamlining (most organizations follow a pretty regular order with a few outliers) but ran out of time. | Recruiting
CHG01397 | Add disposition reasons to the Initial Review step in the Job Application business process | We have received requests from many members asking for additional disposition reasons. When a Supervisory Organization is initially dispositioning candidates, they do not want to have to move the candidates to another stage just to decline them. Many of our managers are the Recruiting Coordinators of their Supervisory Organizations, so it is extra work for the Supervisory Organization because they are essentially screening the candidates twice. | Recruiting |  | Voted NOT to proceed via Doodle poll to Advisory Council
CHG01630 | Request to add salary question to Job Application Template | Request to add salary question to Job Application Template Working Group recommends No Discussion points - It provides a place for discussion with a candidate about salary expectations prior to getting too deep in the process - Managers like it - It presents unconscious bias which is challenging, especially when dealing with protected classes - We should be paying according to the position, not the person - If needed, this discussion can happen during the interview phase | Recruiting
CHG01511 | Validate Hire for proper case format of names | Add validation to Hire and Legal Name Change to require users to enter proper case format of names. This will eliminate errors in integrations and other downstream systems and provide for a more consistent and user-friendly experience. | Staffing