## HCM Roadmap October 2023
ID | Parent ID | Due | Type | Title | Description | Priority
23658550 | NA | NA | Absence Management | Create custom reports so UIN can be added | Create custom reports of Workers on Leave, Workers Returning from Leave and Workers Returned from Leave reports so that UIN can be added | 2
23658688 | 24048197 | N/A | Absence Management | Update Absence Partner To Do in Change Job business process | Currently the "Move Time Off Balance" To Do only triggers if the Employee has the Faculty Vacation Freeze Other ID. Update the To Do so it triggers for all cases of a faculty moving to or from a 12 month annual work period. Update text so it covers all scenarios of change in faculty vacation eligibility. | 2
23697303 | 23791242 | NA | Absence Management | Create notification to Absence Partner when employee has taken greater than 3 days of sick time | Report with alert, running bi-weekly so that Absence Partners can follow up if a note from the doctor is required. Note- a report exists to identify these absences, this would create an inbox item to the Absence Partner. System members could opt to not be included in this report/notification. | 2
23658524 | NA | NA | Absence Management | Create notification to Employee to warn of upcoming expiration of State Comp Time | Report with alert, running monthly to notify employees of State Comp Time expiring in the next two months so they can utilize it before it expires. System members could opt to not be included in this report/notification. | 2
23658544 | NA | NA | Absence Management | Create notification to Employee when they will become eligible to use vacation | Create report with alert, sent at the beginning of the month to employee's whose Time Off Service Date is in the month. System members could opt to not be included in this report/notification. | 3
23757373 | NA | NA | Absence Management | RFP for FMLA software tracking | Several system members expressed interested in a potential shared services contract for FMLA tracking software. This request is seeking approval to begin the RFP process. | 1
23658602 | 24105752 | NA | Absence Management | Move Absence Partner To Do to after completion step in termination business process | Move Absence Partner To Do "Ensure all time off requests entered/donation to sick pool" to after Termination business process completion step. Most working group members agreed to combine it with the "Determine Time Off Payout" step that already exists after the bp completion. Some System Members expressed a need for separate To Dos as dept Abs Partners do some of the steps and central Abs Partners do the rest. Opt in /opt out for two versus one is possible. | 2
23658257 | 24057350 | NA | Performance | Updates to Performance Review Acknowledgement Audit report | Add: UIN, Employee Worker Type, Position Restrictions, Manager Title, Overall Rating and Employee Comments on acknowledgement. Add option to run report only for employees who disagree with review. | 2
23658298 | NA | NA | Recruiting | Turn off Inbox items for Screen step | Opt in/Opt out to turn off the Inbox items for the Screen step. This removes the ability of the Manager to move candidates forward from Screen for those System Members who manage these steps on their behalf. | 2
23658321 | NA | NA | Recruiting | Turn off notifications for the Screen step | Opt in/Opt out to turn off the notifications going to Manager's for the Screen Candidate step. | 1
23658408 | 24058011 | 2023-11-02 | Recruiting | Enable Primary Recruiter role & update reports to include Primary Recruiter if assigned | Enable the Primary Recruiter role so that System Members who wish to assign the role on requisitions for tracking purposes can do so. Update the following reports to include a prompt and column for Primary Recruiter: Job Requisition Aging, Evergreen Job Requisition Aging, Job Requisition Posting Status, Candidate Per Stage, Time to Fill by Position. | 2
23697317 | 24116854 | 2023-11-09 | Recruiting | Revise Change Job and Add Job step routing | Add HR Contact to the roles that are authorized to autocomplete Add Job or Change Job staffing events that originated in Recruiting. Note: which roles can do staffing events are controlled by System Member choices within Staffing. This setting in Recruiting controls whether they can autocomplete if included in the Staffing business processes. | 1
23748351 | 24052970 | 2023-11-02 | Recruiting | Add "Declined Offer - Compensation is insufficient" disposition reason to Background Check step | "Declined Offer - Compensation is insufficient" disposition reason exists on the Offer step in the Job Application business process. There is a request to add this disposition reason to the Background Check step as well for those System Members who do not utilize the offer step within Workday. | 2
23697325 | 23796062 | 2023-09-21 | Recruiting | Remove the Manager's ability to take action from the grid | Remove the ability for the Manager Security role to take any actions from the Candidate grid as this can cause problems with the business process following the required steps. | 1
23697334 | 23796187 | 2023-09-21 | Recruiting | Enable "Active Job Applications" functionality on Candidate Profiles | Add “Active Job Applications” to Candidate Profile for Recruiting Partner/Coordinator/View Only, HR Partner/HR Contact/View Only roles. This allows them to see other positions the Candidate is still active in to make it easier to disposition them from other jobs when they have accepted an offer. View is restricted to areas each role supports. | 2
23784854 | 24132864 | 2023-11-09 | Recruiting | Opt in/Opt out of "Create and/or Manage Interview Settings" To Do in Job Requisition and Job Requisition Change business processes | This step is intended to designate the interview team when a job requisition is being created or changed. The step is frequently skipped. Recommend opt in choice for System Members or eliminating the step if nobody is utilizing it. | 1
23252911 | 23194014 | 2023-10-19 | Recruiting | Create Close Job Requisition Reason "Position Filled" | Working Group Vote on 7/7 to approve the following item: Create a closing reason code of "Position Filled" that will be an option to select when closing a job requisition. | 2
23358441 | 24081471 | 2023-11-02 | Staffing | Contract Contingent Worker Onboarding - Do Not Trigger Edit Passports and Visas & Edit Government IDs Tasks | The staffing working group discussed and voted to no longer trigger the Edit Passport and Visa and Edit Government IDs tasks, in Onboarding, for Contingent Workers. The staffing working group determined that there was no business need to collect Passport, Visa, or Government ID information from contingent workers. | 2
23743897 | 24081743 | 2023-11-09 | Staffing | Modify Change Job Steps Routing to Initiator | The Staffing Working Group discussed and voted to modify the routing of steps in Change Job that go to the initiating group. Routing will be changed to go to the HR Partner or HR Contact based on member selection to ensure the security group with the relevant information receives the step. Steps being modified: q - Update Position Restriction Default Compensation | 2
23744077 | 24084159 | 2023-11-09 | Staffing | Modify Add Additional Job Steps Routing to Initiator | The Staffing Working Group discussed and voted to modify the routing of steps in Add Additional Job that go to the initiating group. Routing will be changed to go to the HR Partner or HR Contact based on member selection to ensure the security group with the relevant information receives the step. Steps being Modified: b - Propose Compensation Hire | 2
23744173 | 24103623 | 2023-11-09 | Staffing | Modify End Additional Job Steps Routing to Initiator | The Staffing Working Group discussed and voted to modify the routing of steps in End Additional Job that go to the initiating group. Routing will be changed to go to the HR Partner or HR Contact based on member selection to ensure the security group with the relevant information receives the step. Steps being modified: d - Assign Roles to Worker e - Offboarding Procedure | 3
23746404 | 24081621 | 2023-11-02 | Staffing | Add Warning in Termination for 5 Year NEFR Policy | The Staffing Working Group discussed and voted to add a warning validation to the Termination BP when a terminating employee is marked as Not Eligible for Rehire. The warning will remind the processor of the 5-year policy associated with being marked Not Eligible for Rehire and provide an explanation (clarification) of the date field in the NEFR report. | 2
23746620 | 24103971 | 2023-11-30 | Staffing | Add HR Partner to Alert 30 Days Before Flexible Work Arrangement Expiration | The Staffing Working Group discussed and voted to add HR Partners to the existing Alert that triggers 30 days before the expiration of a Flexible Work Arrangement. Currently the Alert goes to the employee and their manager. HR Partner will be able to assist departments in efficiently monitoring Flexible Work Arrangements activity. | 2
23747010 | 24104177 | NA | Staffing | Implementation of HR Hub | Implement new feature: HR Hub - The HR Hub provides HR partners with a single point of access to organized workforce movement and actionable information, as well as reports and dashboards most relevant to their work. The HR Hub can include an overview page, actionable reports, HR dashboard, suggested links to external sites or dashboards, and announcements. It also displays incoming and exiting workers that can be filtered by time frames and worker types. | 3
23852085 | 24042334 | 2023-10-19 | Staffing | Remove Hire Compliance Checklist and Move Education Verification to Existing To Do | The Staffing Working Group discussed and voted to remove the Hire Compliance Checklist from the Hire business process. All of the items listed in the Hire Compliance Checklist except for Education Verification are also located in the existing To Do later in the business process. Education Verification will be added to that To Do. Removing the Hire Compliance Checklist and adding Education Verification to the existing To Do will prevent HR Staff from having to duplicate efforts when processing a Hire. | 1
23852307 | 24085674 | 2023-11-09 | Staffing | Member Opt-in/out Form I-9 To Do(s) in Hire | The I-9 and Staffing Working Groups discussed and voted to make the To Do: Complete Form I-9 in Guardian and To Do: Complete Form I-9 Section 3 for Rehire optional in the Hire business process. The I-9 Working Group determined that, for some members, the I-9 is already completed in Guardian by the time the To Do triggers. In addition, the Onboarding business process contains a To Do that lists the Form I-9 as an item that needs to be verified before marking the employee's Onboarding as completed. Making the To Dos in Hire optional based on member selection will allow members to progress through the Hire process more efficiently. | 1
23852641 | 24108398 | NA | Staffing | Extend 45-Day Hire Window to 60 Days | The Staffing Working Group discussed and voted to extend the 45-day hire window to 60 days. Extending the window will give pre-hires additional time to complete their Onboarding process. | 1
23697341 | 23774048 | 2023-09-21 | Talent | Remove Employee To Do in Goal Setting business process | Remove the To Do step for the Employee in the goal setting business process. This step currently triggers to employees after the manager reviews and approves the goals. | 2
23697356 | 23773854 | 2023-10-05 | Talent | Remove Performance Review business process due dates | Remove the due dates on the Performance Review business process as System Members give Employees and Managers different timelines and the dates on the business process cause confusion to users. | 1